## Slide 1
Learning, Evaluation & Analysis Platform
Overview

## Slide 2: LEAP Problem Statement
3 problems:
  Unstandardized databases complicated data usage
  Deliverables, documents and dashboards uneven across projects
  MERL pages not very “friendly”/useful
  Capisc not sufficient for project needs
Since 2013, LEAP!
Notes: Add a picture! ;)

## Slide 3: LEAP conceptual framework

## Slide 4: International Development – Time allocation
OBTAIN
& CLEAN DATA
CALCULATE REQUIRED
DATA
ORGANIZE AND STORE DATA
EXPLORE & LEARN
PRE-LEAP TIME SPENT
OBTAIN
& CLEAN DATA
CALCULATE REQUIRED
DATA
ORGANIZE AND STORE DATA
EXPLORE & LEARN
VALUE
OBTAIN
& CLEAN DATA
CALCULATE REQUIRED
DATA
ORGANIZE AND STORE DATA
EXPLORE & LEARN
WHAT DONORS WANT

## Slide 5: Need to change how to invest time
OBTAIN & CLEAN DATA
CALCULATE REQUIRED
DATA
ORGANIZE AND STORE DATA
EXPLORE & LEARN
CALCULATE REQUIRED
DATA
EXPLORE & LEARN
CALCULATE REQUIRED
DATA
EXPLORE & LEARN
CALCULATE REQUIRED
DATA
EXPLORE & LEARN
Annual Survey
OBTAIN & CLEAN DATA
ORGANIZE AND STORE DATA
Annual Survey
CALCULATE REQUIRED
DATA
EXPLORE & LEARN
CALCULATE REQUIRED
DATA
CALCULATE REQUIRED
DATA
CALCULATE REQUIRED
DATA

## Slide 6: What is the LEAP strategy?
People = 10-day training + Remote support
Process = MERL Policy + Follow-up
Tools = Standard database + automated reports + SharePoint page

## Slide 7: Learning, Evaluation & Analysis Platform (LEAP)
FACILITATES PROJECT MANAGEMENT
  Standardized project management checks, facilitates adaptive management
AUTOMATES REPORTING REQUIREMENTS
  Automatically generated IPTT
EXPOSES DIGESTED DATA
  Adaptive management / data-driven leadership
EXPOSES RAW DATA
  Corporate and cross-Project analysis & project cross-pollination
PROVIDES STANDARDIZED ASSET MANAGEMENT
  Facilitates support, ensures audit compliance, insures against
  staff turnover

## Slide 8
I theorize that
A  B. Let me check
Indicators
PIRS
PMELP
ToC
Etc…
WITH NO RAW DATA MANAGEMENT SYSTEM 
FAIL
Oh well, at least I respected my PMELP
I theorize that
A  B. Let me check
Huh… that’s interesting. I wonder if…
WITH A WELL FUNCTIONING RAW DATA MANAGEMENT SYSTEM 
Indicators
PIRS
PMELP
ToC
Etc…
FAIL
FRESH
LOOK
THE ACTUAL DATA
ANALYSIS
WINS +
LEARNING!!

## Slide 9: Raw data mgmt. example
Beneficiaries
Trained
Applied Tech
Indicators:
Bens Trained:
- Actual = 5
- Target = 5
- Percent = 100%
Applied Tech:
- Actual = 3
- Target = 5
- Percent = 60%
Near roads
Not-near roads
Gender? Age Group? Near Market? Near water? Local politics?
data is not a reporting
obligation,
it’s an opportunity

## Slide 10
FULL
DETAILS
RESPONSIBLE: PROJECT STAFF
RESPONSIBLE: REGIONAL STAFF
checks
FAST &
EASY

## Slide 12: Global LEAP Leads
International MIS Specialists
Project Startup
Follow-on trips (on request)
Remote tech support
Upgrades/improvements
International M&E Specialists
Follow-up support
System QC and monitoring
Amit Kohli
Director S
&
T
Jeremy Barnes
Director S
&
T
Silimane Ngoma
Regional Director MERL
Niri Ramasinjatovo
Senior Director MERL
+ 27 Project experts!

## Slide 13
Finding a project’s LEAP Site and description of LEAP Landing page

## Slide 14: Finding a Project’s LEAP – AV Intranet
https://acdivoca.sharepoint.com/sites/Intranet

## Slide 15: Finding a Project’s LEAP – Projects
https://acdivoca.sharepoint.com/sites/Intranet/projects
Select the country

## Slide 16: Finding a Project’s LEAP – Country Page
Select the project

## Slide 17: Finding a Project’s LEAP – Project Page
Click Project LEAP

## Slide 18: Project LEAP Landing Page

## Slide 19: LEAP Landing Page – MIS Administrators
Responsible for:
Project M&E Data Management
Visualization & Analytics
Ad Hoc Queries

## Slide 20: LEAP Landing Page – Theory of Change

## Slide 21: LEAP Landing Page – Dashboards

## Slide 22: LEAP Landing Page – Learning & Impacts

## Slide 23: LEAP Landing Page – Filing Cabinet

## Slide 24: LEAP Landing Page – Database Summaries
Top-level view of all project data
Measurement according to current year’s time lapse

## Slide 25: LEAP Landing Page – Database Updates
Flow of information arriving into the MIS
If activities are being implemented, data should be increasing
Flat lines are meaningful, but not always bad!

## Slide 26
Indicator Tally & Bullet Chart

## Slide 27: Indicator Tally – Navigation
Click Live Indicator Tally

## Slide 28: Indicator Tally – Automated IPTT
Note the date of calculation!
Indicators and performance (target, actual, % achieved) by FY and LoP
Get Excel Copy

## Slide 29: Indicator Tally – Automated IPTT
Output achievement with time lapse
How much is needed to be “current”
Status 2 weeks ago
Value added last 2 weeks

## Slide 30: Indicator Tally – Interpretation
Examples:
Some activities may be planned for later in the year (slow for several months then a surge)
Situation on the ground halts activities
Target achievement is not always linear, so slow movement not always a sign of bad performance!

## Slide 31: What do we need from project staff?
Upload ALL data
Work with us to ensure automated queries are correct
Use it! 

## Slide 32
M&E Deliverables
Follow-up on M&E Obligations
  Hard:
    Contractual Obligations (Annual Report, Database created, …)
  Soft:
    Intermediate goals for Hard deadlines
    Action Point items: (DQA findings, MIS findings, …)
Database here!

## Slide 33
Project selector
Soft/Hard Deadlines
PY selector
Milestone Timeline

## Slide 35: What do we need from project staff?
Upload all deliverables to Filing Cabinet
Ensure Due dates are correct
Ensure Milestones “apply”
Enter in when deliverables are “In-progress” & “Finalized”
Use it! 

## Slide 36
Future initiatives

## Slide 37
DISAGGREGATES IN AUTOMATED IPTT

## Slide 38
Other Future initiatives
Quarterly Reports?
Power View  Power BI
Simplified calcs for Project Staff

## Slide 39
Data Stories & Power BI demo

## Slide 40
LEAP Summary
People = Project staff & HQ staff
Process = Trainings, DQAs, Backend updater
Tools = Project databases – Raw data, LEAP Sites, Dashboards, automated reports
OUR GOAL:
Everything you need to make decisions on your M&E data ->
Work planning, Adaptive Management, Proactive Adaptation

## Slide 41
Small Group / Brainstorm
How can your team use LEAP assets
WEEKLY?
Missing anything? For example:

## Slide 42
Example 1,
Data completeness report?

## Slide 43
Example 2,
Full-Year Views

## Slide 44
Current LEAP Automatic Assets
Auto-IPTT
Indicator
Summaries
Indicator Performance
Data Uploads
Milestone & Action Point Tracker
Indicator History?
+ Project dashboards!

## Slide 45
Thanks!